## Projects_Master
Project Name | Owner | Start Date | Target Date | Current Sprint | Overall Progress % | Frontend % | Backend % | Database % | Testing % | Deployment % | Current Status | Health Status | Expected Completion
IntelliMailPilot / EmailBot | Akshay / Full-stack | 23-06-2026 | 05-10-2026 | Sprint 1 - Stabilization and QA Foundation | 57 | 74 | 70 | 71 | 24 | 43 | Active stabilization | Yellow | 2026-10-05 (planning baseline; depends on QA capacity)

## Daily_Updates
Date | Developer | Project | Sprint | Page | Module | Submodule | Task ID | Task Description | Frontend Status | Backend Status | Database Status | API Status | Testing Status | Priority | Estimated Hours | Actual Hours | Completion % | Current Status | Blockers | Start Date | Target Date | Remarks | This Week Completed | This Week Update | Next Week Plan | Google Sheet Import Status
25-06-2026 | Akshay / Full-stack | Project Management | Sprint 1 | All | Architecture | Baseline | IMP-001 | Create durable project baseline and Google Sheets import pack | Completed | Completed | Completed | Completed | Completed | Critical | 8 | 8 | 100 | Completed |  | 22-06-2026 | 22-06-2026 | 15 trackers, reports, state file | Yes | Completed - 100% |  | Auto-filled from project tracker
25-06-2026 | Akshay / Full-stack | Campaign Workflow | Sprint 1 | Dashboard | Schedule Modal | Schedule Details | IMP-002 | Finish four-column schedule details layout and six-column delivery settings | In Progress | N/A | N/A | N/A | In Progress | High | 4 |  | 80 | In Progress | Current uncommitted workflow changes | 22-06-2026 | 23-06-2026 | Stable schedule modal across desktop/mobile |  | In Progress - 80% |  | Auto-filled from project tracker
25-06-2026 | Akshay / Full-stack | Engineering Quality | Sprint 1 | All | Linting | ESLint | IMP-003 | Commit a non-interactive ESLint configuration and resolve baseline violations | Not Started | Not Started | N/A | Not Started | Not Started | Critical | 8 |  | 0 | Not Started |  | 22-06-2026 | 24-06-2026 | npm run lint passes unattended |  | Not Started - 0% |  | Auto-filled from project tracker
25-06-2026 | Akshay / Full-stack | Engineering Quality | Sprint 1 | All | Build | Production Build | IMP-004 | Run clean production build and document warnings | Not Started | Not Started | Not Started | Not Started | Not Started | Critical | 6 |  | 0 | Not Started | IMP-002, IMP-003 | 23-06-2026 | 24-06-2026 | next build succeeds cleanly |  | Not Started - 0% |  | Auto-filled from project tracker
25-06-2026 | Akshay / Full-stack | QA Foundation | Sprint 1 | All | Testing | Test Strategy | IMP-005 | Define test pyramid, fixtures, environments, and release gates | Not Started | Not Started | Not Started | Not Started | Not Started | Critical | 8 |  | 0 | Not Started | IMP-001 | 23-06-2026 | 25-06-2026 | Approved QA strategy |  | Not Started - 0% |  | Auto-filled from project tracker
25-06-2026 | Akshay / Full-stack | Authentication | Sprint 1 | Login and account pages | Auth | RBAC | IMP-006 | Automate login, logout, session, role routing, pending and disabled account flows | Not Started | Not Started | Not Started | Not Started | Not Started | Critical | 18 |  | 0 | Not Started | IMP-005 | 24-06-2026 | 29-06-2026 | Verified USER/MANAGER/ADMIN access matrix |  | Not Started - 0% | Planned / continues next week | Auto-filled from project tracker
25-06-2026 | Akshay / Full-stack | Security | Sprint 1 | All | Secrets and Tokens | Security Audit | IMP-007 | Audit cookie flags, JWT expiry, token crypto, password reset and secret handling | Not Started | Not Started | Not Started | Not Started | Not Started | Critical | 20 |  | 0 | Not Started | IMP-006 | 26-06-2026 | 02-07-2026 | Security findings closed or accepted |  | Not Started - 0% | Planned / continues next week | Auto-filled from project tracker
25-06-2026 | Akshay / Full-stack | Client Data | Sprint 1 | Client Data | Upload | File Validation | IMP-008 | Harden XLSX/CSV upload, preview, commit and validation errors | In Progress | In Progress | In Progress | In Progress | In Progress | High | 24 |  | 70 | In Progress | IMP-005 | 25-06-2026 | 02-07-2026 | Reliable upload pipeline |  | In Progress - 70% | Planned / continues next week | Auto-filled from project tracker
25-06-2026 | Akshay / Full-stack | Client Data | Sprint 1 | Client List | Records | CRUD and Duplicates | IMP-009 | Verify bulk edit/delete, duplicate detection, bin and restore workflows | In Progress | In Progress | In Progress | In Progress | In Progress | High | 28 |  | 68 | In Progress | IMP-008 | 28-06-2026 | 06-07-2026 | Data operations are reversible and scoped |  | In Progress - 68% | Planned / continues next week | Auto-filled from project tracker
25-06-2026 | Akshay / Full-stack | Drafts | Sprint 1 | Drafts | Editor | Rich Text | IMP-010 | Stabilize draft editor, templates, file text extraction and preview | In Progress | In Progress | In Progress | In Progress | In Progress | High | 24 |  | 75 | In Progress | IMP-005 | 29-06-2026 | 06-07-2026 | Safe reusable draft workflow |  |  | Planned / continues next week | Auto-filled from project tracker
25-06-2026 | Akshay / Full-stack | Campaigns | Sprint 1 | Campaign Wizard | Creation | Preflight | IMP-011 | Validate audience, sender, content, credits and scheduling before creation | In Progress | In Progress | In Progress | In Progress | In Progress | Critical | 30 |  | 72 | In Progress | IMP-006, IMP-008, IMP-010 | 30-06-2026 | 09-07-2026 | Campaign creation cannot enter invalid state |  |  | Planned / continues next week | Auto-filled from project tracker
25-06-2026 | Akshay / Full-stack | Campaigns | Sprint 1 | Broadcasts | Execution | Worker Lifecycle | IMP-012 | Test queue, locks, heartbeat, stale recovery, pause, resume, stop and completion | In Progress | In Progress | In Progress | In Progress | In Progress | Critical | 40 |  | 65 | In Progress | IMP-011 | 04-07-2026 | 16-07-2026 | Recoverable exactly-once-oriented execution |  |  | Planned / continues next week | Auto-filled from project tracker
25-06-2026 | Akshay / Full-stack | Campaigns | Roadmap Backlog | Broadcasts | Delivery | Recipient Safety | IMP-013 | Verify recipient claims, global send locks, dedupe and retry classification | In Progress | In Progress | In Progress | In Progress | In Progress | Critical | 32 |  | 62 | In Progress | IMP-012 | 09-07-2026 | 20-07-2026 | No accidental duplicate sends |  |  |  | Auto-filled from project tracker
25-06-2026 | Akshay / Full-stack | Campaigns | Roadmap Backlog | Reports | Tracking | Open/Click/Reply | IMP-014 | Validate tracking pixels, event endpoints, reply sync and campaign attribution | In Progress | In Progress | In Progress | In Progress | In Progress | High | 28 |  | 65 | In Progress | IMP-012 | 14-07-2026 | 25-07-2026 | Trustworthy campaign analytics |  |  |  | Auto-filled from project tracker
25-06-2026 | Akshay / Full-stack | Mail Accounts | Sprint 1 | Sender Emails | Connections | SMTP and Graph | IMP-015 | Stabilize sender account creation, OAuth callback, token refresh and status | In Progress | In Progress | In Progress | In Progress | In Progress | Critical | 36 |  | 70 | In Progress | IMP-006 | 06-07-2026 | 20-07-2026 | Reliable connected sender accounts |  |  |  | Auto-filled from project tracker
25-06-2026 | Akshay / Full-stack | Mailbox | Roadmap Backlog | Master Inbox | Messages | Unified Inbox | IMP-016 | Validate folder sync, cache, pagination, read/archive/delete/reply/forward/send | In Progress | In Progress | In Progress | In Progress | In Progress | High | 40 |  | 68 | In Progress | IMP-015 | 17-07-2026 | 01-08-2026 | Consistent inbox across supported providers |  |  |  | Auto-filled from project tracker
25-06-2026 | Akshay / Full-stack | Warm-up | Roadmap Backlog | Warm-up | Automation | Conversations | IMP-017 | Validate sheets, senders, conversations, run-next, pause/stop and auto replies | In Progress | In Progress | In Progress | In Progress | In Progress | High | 40 |  | 60 | In Progress | IMP-015 | 21-07-2026 | 06-08-2026 | Controlled and auditable warm-up engine |  |  |  | Auto-filled from project tracker
25-06-2026 | Akshay / Full-stack | Admin | Roadmap Backlog | Admin Dashboard | User Management | Lifecycle | IMP-018 | Test request approval, status, password reset, subscription and scoped resource views | In Progress | In Progress | In Progress | In Progress | In Progress | High | 30 |  | 72 | In Progress | IMP-006 | 22-07-2026 | 03-08-2026 | Safe admin operations |  |  |  | Auto-filled from project tracker
25-06-2026 | Akshay / Full-stack | Billing | Roadmap Backlog | Profile and Admin | Credits | Ledger | IMP-019 | Validate subscriptions, upgrades, invoices, credit reservation and reports | In Progress | In Progress | In Progress | In Progress | In Progress | Critical | 32 |  | 66 | In Progress | IMP-012 | 27-07-2026 | 10-08-2026 | Auditable credit accounting |  |  |  | Auto-filled from project tracker
25-06-2026 | Akshay / Full-stack | Reporting | Roadmap Backlog | Reports and Summary | Analytics | Dashboards | IMP-020 | Reconcile dashboard, campaign, project, sender, warm-up and credit metrics | In Progress | In Progress | In Progress | In Progress | In Progress | High | 36 |  | 64 | In Progress | IMP-014, IMP-019 | 01-08-2026 | 17-08-2026 | Consistent stakeholder reporting |  |  |  | Auto-filled from project tracker
25-06-2026 | Akshay / Full-stack | Productivity | Roadmap Backlog | Dashboard | Tasks and Calendar | Planning | IMP-021 | Validate timeline tasks, calendar events, work updates and approvals | In Progress | In Progress | In Progress | In Progress | In Progress | Medium | 28 |  | 70 | In Progress | IMP-006 | 06-08-2026 | 19-08-2026 | Reliable internal planning workflow |  |  |  | Auto-filled from project tracker
25-06-2026 | Akshay / Full-stack | Performance | Roadmap Backlog | All | Frontend | Bundle and Rendering | IMP-022 | Profile large dashboard component, CSS size, rerenders and route payloads | Not Started | Not Started | N/A | Not Started | Not Started | High | 40 |  | 0 | Not Started | IMP-004 | 11-08-2026 | 27-08-2026 | Measured performance budget achieved |  |  |  | Auto-filled from project tracker
25-06-2026 | Akshay / Full-stack | Performance | Roadmap Backlog | All | Backend | Database Queries | IMP-023 | Profile slow queries and validate indexes for campaign, client data, inbox and reports | N/A | Not Started | Not Started | Not Started | Not Started | High | 36 |  | 0 | Not Started | IMP-012, IMP-016, IMP-020 | 15-08-2026 | 31-08-2026 | Documented query SLOs |  |  |  | Auto-filled from project tracker
25-06-2026 | Akshay / Full-stack | Observability | Roadmap Backlog | Operations | Logging | Health and Alerts | IMP-024 | Standardize structured logs, correlation IDs, worker health, queue alerts and dashboards | Not Started | Not Started | Not Started | Not Started | Not Started | High | 32 |  | 0 | Not Started | IMP-012 | 21-08-2026 | 05-09-2026 | Actionable production telemetry |  |  |  | Auto-filled from project tracker
25-06-2026 | Akshay / Full-stack | CI/CD | Roadmap Backlog | Repository | Pipeline | Quality Gates | IMP-025 | Add install, lint, test, build, secret scan and artifact checks | Not Started | Not Started | Not Started | Not Started | Not Started | Critical | 28 |  | 0 | Not Started | IMP-003, IMP-005 | 24-08-2026 | 07-09-2026 | Every change gets repeatable validation |  |  |  | Auto-filled from project tracker
25-06-2026 | Akshay / Full-stack | Deployment | Roadmap Backlog | AWS ECS | Web and Worker | Immutable Release | IMP-026 | Validate Docker build, ECS task definitions, secrets, rollbacks and worker singleton | In Progress | In Progress | In Progress | In Progress | In Progress | Critical | 36 |  | 45 | In Progress | IMP-024, IMP-025 | 31-08-2026 | 14-09-2026 | Repeatable staging deployment |  |  |  | Auto-filled from project tracker
25-06-2026 | Akshay / Full-stack | Data Reliability | Roadmap Backlog | MongoDB | Recovery | Backup and Migration | IMP-027 | Create schema migration policy, backup/restore test and data retention rules | N/A | Not Started | Not Started | Not Started | Not Started | Critical | 32 |  | 0 | Not Started | IMP-023 | 29-08-2026 | 12-09-2026 | Proven recovery procedure |  |  |  | Auto-filled from project tracker
25-06-2026 | Akshay / Full-stack | Legacy Cleanup | Roadmap Backlog | Repository | Legacy Apps | Decommission | IMP-028 | Decide and execute retirement path for legacy dashboard, Python automation and standalone campaign engine | Not Started | Not Started | Not Started | Not Started | Not Started | Medium | 24 |  | 0 | Not Started | IMP-026, IMP-027 | 05-09-2026 | 18-09-2026 | Single supported production architecture |  |  |  | Auto-filled from project tracker
25-06-2026 | Akshay / Full-stack | Accessibility | Roadmap Backlog | All Pages | UI | WCAG | IMP-029 | Complete keyboard, focus, contrast, labels, modal and reduced-motion audit | Not Started | N/A | N/A | N/A | Not Started | High | 36 |  | 0 | Not Started | IMP-004 | 19-08-2026 | 06-09-2026 | WCAG 2.1 AA critical paths |  |  |  | Auto-filled from project tracker
25-06-2026 | Akshay / Full-stack | Responsive UI | Sprint 1 | All Pages | UI | Viewport Matrix | IMP-030 | Execute manual QA at 320, 375, 430, 768, 1024, 1280, 1440 and 1920 pixels | In Progress | N/A | N/A | N/A | In Progress | High | 32 |  | 35 | In Progress | IMP-002, IMP-004 | 24-06-2026 | 04-07-2026 | Signed responsive test matrix |  | In Progress - 35% | Planned / continues next week | Auto-filled from project tracker
25-06-2026 | Akshay / Full-stack | Release | Roadmap Backlog | All | UAT | Business Acceptance | IMP-031 | Run role-based UAT with realistic data and production-like sender accounts | Not Started | Not Started | Not Started | Not Started | Not Started | Critical | 40 |  | 0 | Not Started | IMP-006 through IMP-030 | 08-09-2026 | 22-09-2026 | Signed UAT report |  |  |  | Auto-filled from project tracker
25-06-2026 | Akshay / Full-stack | Release | Roadmap Backlog | Production | Go-live | Release Candidate | IMP-032 | Freeze scope, close critical defects, rehearse rollback and deploy | Not Started | Not Started | Not Started | Not Started | Not Started | Critical | 32 |  | 0 | Not Started | IMP-031 | 20-09-2026 | 26-09-2026 | Production release with rollback readiness |  |  |  | Auto-filled from project tracker
25-06-2026 | Akshay / Full-stack | Release | Roadmap Backlog | Production | Hypercare | Stabilization | IMP-033 | Monitor delivery, errors, credits, worker queues and inbox sync after launch | Not Started | Not Started | Not Started | Not Started | Not Started | High | 40 |  | 0 | Not Started | IMP-032 | 27-09-2026 | 04-10-2026 | Stable seven-day production window |  |  |  | Auto-filled from project tracker
25-06-2026 | Akshay / Full-stack | Project Management | Sprint 1 | All | Google Sheets Import | Excel Date Format | IMP-034 | Fix Excel and Google Sheets import date formatting and weekly auto-fill summaries | Completed | N/A | N/A | N/A | Completed | High | 4 | 4 | 100 | Completed | IMP-001 | 23-06-2026 | 24-06-2026 | Existing workbook, CSV tabs, ZIP packs, and extracted import folders show exact yyyy-mm-dd dates | Yes | Completed - 100% |  | Auto-filled from project tracker

## Daily_Task_Planner
Task ID | Today's Tasks | Tomorrow Tasks | Day After Tomorrow Tasks | This Week Update | Next Week Plan | Estimated Hours | Priority | Dependencies | Status
IMP-002 | Pending update: Finish four-column schedule details layout and six-column delivery settings |  |  | In Progress - 80% |  | 4 | High | Current uncommitted workflow changes | Pending Update
IMP-003 | Pending update: Commit a non-interactive ESLint configuration and resolve baseline violations |  |  | Not Started - 0% |  | 8 | Critical | None | Pending Update
IMP-004 | Pending update: Run clean production build and document warnings |  |  | Not Started - 0% |  | 6 | Critical | IMP-002, IMP-003 | Pending Update
IMP-005 | Define test pyramid, fixtures, environments, and release gates |  |  | Not Started - 0% |  | 8 | Critical | IMP-001 | Not Started
IMP-006 | Automate login, logout, session, role routing, pending and disabled account flows |  |  | Not Started - 0% | Automate login, logout, session, role routing, pending and disabled account flows | 18 | Critical | IMP-005 | Not Started
IMP-007 |  | Audit cookie flags, JWT expiry, token crypto, password reset and secret handling |  | Not Started - 0% | Audit cookie flags, JWT expiry, token crypto, password reset and secret handling | 20 | Critical | IMP-006 | Not Started
IMP-008 | Harden XLSX/CSV upload, preview, commit and validation errors |  |  | In Progress - 70% | Harden XLSX/CSV upload, preview, commit and validation errors | 24 | High | IMP-005 | In Progress
IMP-009 |  |  |  | In Progress - 68% | Verify bulk edit/delete, duplicate detection, bin and restore workflows | 28 | High | IMP-008 | In Progress
IMP-010 |  |  |  |  | Stabilize draft editor, templates, file text extraction and preview | 24 | High | IMP-005 | In Progress
IMP-011 |  |  |  |  | Validate audience, sender, content, credits and scheduling before creation | 30 | Critical | IMP-006, IMP-008, IMP-010 | In Progress
IMP-012 |  |  |  |  | Test queue, locks, heartbeat, stale recovery, pause, resume, stop and completion | 40 | Critical | IMP-011 | In Progress
IMP-013 | [5 empty] | 32 | Critical | IMP-012 | In Progress
IMP-014 | [5 empty] | 28 | High | IMP-012 | In Progress
IMP-015 | [5 empty] | 36 | Critical | IMP-006 | In Progress
IMP-016 | [5 empty] | 40 | High | IMP-015 | In Progress
IMP-017 | [5 empty] | 40 | High | IMP-015 | In Progress
IMP-018 | [5 empty] | 30 | High | IMP-006 | In Progress
IMP-019 | [5 empty] | 32 | Critical | IMP-012 | In Progress
IMP-020 | [5 empty] | 36 | High | IMP-014, IMP-019 | In Progress
IMP-021 | [5 empty] | 28 | Medium | IMP-006 | In Progress
IMP-022 | [5 empty] | 40 | High | IMP-004 | Not Started
IMP-023 | [5 empty] | 36 | High | IMP-012, IMP-016, IMP-020 | Not Started
IMP-024 | [5 empty] | 32 | High | IMP-012 | Not Started
IMP-025 | [5 empty] | 28 | Critical | IMP-003, IMP-005 | Not Started
IMP-026 | [5 empty] | 36 | Critical | IMP-024, IMP-025 | In Progress
IMP-027 | [5 empty] | 32 | Critical | IMP-023 | Not Started
IMP-028 | [5 empty] | 24 | Medium | IMP-026, IMP-027 | Not Started
IMP-029 | [5 empty] | 36 | High | IMP-004 | Not Started
IMP-030 | Execute manual QA at 320, 375, 430, 768, 1024, 1280, 1440 and 1920 pixels |  |  | In Progress - 35% | Execute manual QA at 320, 375, 430, 768, 1024, 1280, 1440 and 1920 pixels | 32 | High | IMP-002, IMP-004 | In Progress
IMP-031 | [5 empty] | 40 | Critical | IMP-006 through IMP-030 | Not Started
IMP-032 | [5 empty] | 32 | Critical | IMP-031 | Not Started
IMP-033 | [5 empty] | 40 | High | IMP-032 | Not Started

## Weekly_Roadmap
Week Number | Feature | Page | Module | Owner | Planned Hours | Actual Hours | Dependencies | Target Date | Completion % | Status | Completed This Week | Updated This Week | Next Week Planned | Next Week Completion Target | Remarks
Week 1 | IMP-001, IMP-002, IMP-003, IMP-004, IMP-005, IMP-006, IMP-007, IMP-008, IMP-009, IMP-030, IMP-034 | All, Dashboard, Login and account pages, Client Data, Client List, All Pages | Architecture, Schedule Modal, Linting, Build, Testing, Auth, Secrets and Tokens, Upload, Records, UI, Google Sheets Import | Akshay / Full-stack | 160 |  | Current uncommitted workflow changes; IMP-002, IMP-003; IMP-001; IMP-005; IMP-006; IMP-008; IMP-002, IMP-004 | 28-06-2026 | 41 | In Progress | IMP-001: Create durable project baseline and Google Sheets import pack ¦ IMP-034: Fix Excel and Google Sheets import date formatting and weekly auto-fill summaries | IMP-002: Finish four-column schedule details layout and six-column delivery settings ¦ IMP-008: Harden XLSX/CSV upload, preview, commit and validation errors ¦ IMP-009: Verify bulk edit/delete, duplicate detection, bin and restore workflows ¦ IMP-030: Execute manual QA at 320, 375, 430, 768, 1024, 1280, 1440 and 1920 pixels ¦ IMP-003: Commit a non-interactive ESLint configuration and resolve baseline violations ¦ IMP-004: Run clean production build and document warnings ¦ IMP-005: Define test pyramid, fixtures, environments, and release gates ¦ IMP-006: Automate login, logout, session, role routing, pending and disabled account flows ¦ IMP-007: Audit cookie flags, JWT expiry, token crypto, password reset and secret handling |  |  | Stabilize current UI work and establish repeatable quality gates.
Week 2 | IMP-010, IMP-011, IMP-012 | Drafts, Campaign Wizard, Broadcasts | Editor, Creation, Execution | Akshay / Full-stack | 94 |  | IMP-005; IMP-006, IMP-008, IMP-010; IMP-011 | 05-07-2026 | 71 | In Progress |  |  | IMP-006: Automate login, logout, session, role routing, pending and disabled account flows ¦ IMP-007: Audit cookie flags, JWT expiry, token crypto, password reset and secret handling ¦ IMP-008: Harden XLSX/CSV upload, preview, commit and validation errors ¦ IMP-009: Verify bulk edit/delete, duplicate detection, bin and restore workflows ¦ IMP-010: Stabilize draft editor, templates, file text extraction and preview ¦ IMP-011: Validate audience, sender, content, credits and scheduling before creation ¦ IMP-012: Test queue, locks, heartbeat, stale recovery, pause, resume, stop and completion ¦ IMP-030: Execute manual QA at 320, 375, 430, 768, 1024, 1280, 1440 and 1920 pixels | Finish draft/editor stabilization, campaign preflight validation, and start worker lifecycle verification | Sequence may shift after measured QA findings.
Week 3 | IMP-013, IMP-015 | Broadcasts, Sender Emails | Delivery, Connections | Akshay / Full-stack | 68 |  | IMP-012; IMP-006 | 12-07-2026 | 66 | In Progress |  |  |  |  | Sequence may shift after measured QA findings.
Week 4 | IMP-014, IMP-016 | Reports, Master Inbox | Tracking, Messages | Akshay / Full-stack | 68 |  | IMP-012; IMP-015 | 19-07-2026 | 67 | In Progress |  |  |  |  | Sequence may shift after measured QA findings.
Month 2 | IMP-018, IMP-019, IMP-020, IMP-021, IMP-022, IMP-023, IMP-029 | Admin Dashboard, Profile and Admin, Reports and Summary, Dashboard, All, All Pages | User Management, Credits, Analytics, Tasks and Calendar, Frontend, Backend, UI | Akshay / Full-stack | 238 |  | IMP-006; IMP-012; IMP-014, IMP-019; IMP-004; IMP-012, IMP-016, IMP-020 | 20-08-2026 | 39 | In Progress |  |  |  |  | Sequence may shift after measured QA findings.
Month 3 | IMP-024, IMP-025, IMP-026, IMP-027, IMP-028, IMP-031 | Operations, Repository, AWS ECS, MongoDB, All | Logging, Pipeline, Web and Worker, Recovery, Legacy Apps, UAT | Akshay / Full-stack | 192 |  | IMP-012; IMP-003, IMP-005; IMP-024, IMP-025; IMP-023; IMP-026, IMP-027; IMP-006 through IMP-030 | 19-09-2026 | 8 | In Progress |  |  |  |  | Sequence may shift after measured QA findings.
Completion / Hypercare | IMP-032, IMP-033 | Production | Go-live, Hypercare | Akshay / Full-stack | 72 |  | IMP-031; IMP-032 | 04-10-2026 | 0 | Planned |  |  |  |  | Sequence may shift after measured QA findings.

## Sprint_Tracker
Sprint | Features | Completed | In Progress | Pending | Bugs | Testing Status | Release Readiness | Health Status | This Week Completed | Next Week Plan
Sprint 1 (Jun 23-Jul 6) | Baseline, tracker date fix, workflow UI, lint/build, QA strategy, auth start, client data, drafts, campaign preflight | 2 | 4 | 5 | Date serial import fixed; lint/build still pending | Manual / setup | Low | Yellow | IMP-001, IMP-034 | IMP-006, IMP-007, IMP-008, IMP-009, IMP-010, IMP-011, IMP-012, IMP-030
Sprint 2 (Jul 7-Jul 20) | Worker lifecycle, recipient safety, mail accounts, campaign tracking | 0 | 0 | 6 | TBD | Planned | Low | Yellow |  | IMP-012, IMP-013, IMP-015
Sprint 3 (Jul 21-Aug 3) | Worker lifecycle, recipient safety, mail accounts | 0 | 0 | 5 | TBD | Planned | Medium-Low | Yellow
Sprint 4 (Aug 4-Aug 17) | Inbox, warm-up, billing, reporting | 0 | 0 | 5 | TBD | Planned | Medium | Yellow
Sprint 5 (Aug 18-Aug 31) | Performance, accessibility, observability, data reliability | 0 | 0 | 5 | TBD | Planned | Medium | Yellow
Sprint 6 (Sep 1-Sep 14) | CI/CD, ECS staging, legacy cleanup, UAT preparation | 0 | 0 | 5 | TBD | Planned | Medium-High | Yellow
Sprint 7 (Sep 15-Oct 5) | UAT, release candidate, production deployment, hypercare | 0 | 0 | 3 | Exit criterion: no Sev-1/2 | Planned | Target 90%+ | Yellow

## Feature_Tracker
Feature | Frontend | Backend | Database | API | Testing | Deployment | Overall Status | Completion %
Authentication and RBAC | 82 | 78 | 78 | 80 | 25 | 45 | Yellow | 65
Dashboard and role workspaces | 84 | 76 | 70 | 76 | 30 | 45 | Yellow | 64
Client data and lead lists | 80 | 76 | 78 | 78 | 32 | 45 | Yellow | 65
Drafts and templates | 82 | 72 | 72 | 75 | 30 | 45 | Yellow | 63
Campaign workflow | 86 | 74 | 76 | 78 | 35 | 48 | Yellow | 66
Campaign execution worker | 70 | 78 | 76 | 76 | 22 | 48 | Yellow | 62
Sender accounts and OAuth | 74 | 76 | 72 | 78 | 25 | 45 | Yellow | 62
Unified mailbox | 76 | 74 | 74 | 76 | 24 | 42 | Yellow | 61
Warm-up automation | 72 | 70 | 72 | 72 | 20 | 40 | Yellow | 58
Reports and analytics | 78 | 68 | 70 | 72 | 22 | 42 | Yellow | 59
Admin and subscriptions | 78 | 76 | 74 | 78 | 28 | 45 | Yellow | 63
Tasks, calendar and productivity | 76 | 72 | 72 | 74 | 25 | 42 | Yellow | 60
Observability and operations | 45 | 58 | 55 | 60 | 18 | 38 | Red | 46
Automated QA | 20 | 20 | 25 | 20 | 12 | 20 | Red | 20
CI/CD and deployment | 35 | 45 | 50 | 45 | 15 | 45 | Red | 39

## Frontend_Tracker
Page | Module | Components | Framework | Status | Completion %
/account/disabled | account | Link | Next.js 14 / React 18 | Implemented - QA pending | 76
/account/pending | account | Link | Next.js 14 / React 18 | Implemented - QA pending | 76
/campaigns | campaigns | { useCallback, useEffect, useMemo, useRef, useState }; { useRouter }; AppLayout; Badge | Next.js 14 / React 18 | Implemented - QA pending | 76
/change-password | change-password | { useRouter }; { useMemo, useState } | Next.js 14 / React 18 | Implemented - QA pending | 76
/client-data/client-list | client-data | { memo, useCallback, useEffect, useMemo, useRef, useState }; { useRouter }; AppLayout; Badge | Next.js 14 / React 18 | Implemented - QA pending | 76
/client-data | client-data | { redirect } | Next.js 14 / React 18 | Implemented - QA pending | 76
/client-data/upload-sheet | client-data | { redirect } | Next.js 14 / React 18 | Implemented - QA pending | 76
/client-data/uploaded-files | client-data | { redirect } | Next.js 14 / React 18 | Implemented - QA pending | 76
/dashboard/admin | dashboard | { cookies }; { redirect }; RoleDashboardShell; { getAuthCookieName, verifyAuthToken } | Next.js 14 / React 18 | Implemented - QA pending | 82
/dashboard/admin/pending-requests | dashboard | Link; { useEffect, useState } | Next.js 14 / React 18 | Implemented - QA pending | 82
/dashboard/admin/users/:id | dashboard | { useEffect, useState } | Next.js 14 / React 18 | Implemented - dynamic route QA pending | 82
/dashboard/admin/users | dashboard | Link; { useEffect, useState } | Next.js 14 / React 18 | Implemented - QA pending | 82
/dashboard/broadcasts | dashboard | DashboardClientPage | Next.js 14 / React 18 | Implemented - QA pending | 82
/dashboard/manager | dashboard | { cookies }; { redirect }; RoleDashboardShell; { Badge, Button, Card, CardContent, CardDescription, CardHeader, CardTitle, Table, TableBody, TableCell, TableHead, TableHeader, TableRow, TableWrapper } | Next.js 14 / React 18 | Implemented - QA pending | 82
/dashboard | dashboard | { cookies }; { redirect }; { getAuthCookieName, verifyAuthToken }; { getDashboardPathForRole } | Next.js 14 / React 18 | Implemented - QA pending | 82
/dashboard/user | dashboard | DashboardClientPage | Next.js 14 / React 18 | Implemented - QA pending | 82
/dashboard/user/profile/:section | dashboard | UserProfilePage | Next.js 14 / React 18 | Implemented - dynamic route QA pending | 82
/dashboard/user/profile | dashboard | { createPortal }; { useEffect, useMemo, useState }; AppLayout; { useTheme } | Next.js 14 / React 18 | Implemented - QA pending | 82
/draft-templates | draft-templates | { useEffect, useMemo, useState }; AppLayout; Button | Next.js 14 / React 18 | Implemented - QA pending | 76
/drafts/:id | drafts | DraftDetailClientPage | Next.js 14 / React 18 | Implemented - dynamic route QA pending | 76
/drafts | drafts | DraftsClientPage | Next.js 14 / React 18 | Implemented - QA pending | 76
/forgot-password | forgot-password | Link; { useState } | Next.js 14 / React 18 | Implemented - QA pending | 76
/leads | leads | { useEffect, useMemo, useState }; AppLayout; Button | Next.js 14 / React 18 | Implemented - QA pending | 76
/login | login | Link; { useRouter }; { useEffect, useMemo, useState }; { getSeedEmailPlaceholder, getSeedLoginPrefill, normalizeLoginType, TEMP_AUTH_ROLES } | Next.js 14 / React 18 | Implemented - QA pending | 76
/mail-inbox | mail-inbox | { useCallback, useEffect, useMemo, useState }; AppLayout; Button; Badge | Next.js 14 / React 18 | Implemented - QA pending | 76
| Landing | { cookies }; { redirect }; { getAuthCookieName, verifyAuthToken }; { getDashboardPathForRole } | Next.js 14 / React 18 | Implemented - QA pending | 76
/report | report | { useEffect, useMemo, useState }; AppLayout; Button | Next.js 14 / React 18 | Implemented - QA pending | 76
/request-access | request-access | Link; { useState } | Next.js 14 / React 18 | Implemented - QA pending | 76
/reset-password | reset-password | Link; { Suspense, useState }; { useSearchParams } | Next.js 14 / React 18 | Implemented - QA pending | 76
/sender-emails | sender-emails | { useEffect, useState }; AppLayout; Button | Next.js 14 / React 18 | Implemented - QA pending | 76
/summary | summary | Page-local components | Next.js 14 / React 18 | Implemented - QA pending | 76
/unauthorized | unauthorized | { useRouter } | Next.js 14 / React 18 | Implemented - QA pending | 76
/user/master-inbox | user | MailInboxPage | Next.js 14 / React 18 | Implemented - QA pending | 76
/warm-up | warm-up | { useEffect, useMemo, useRef, useState }; AppLayout; Button; { Card, CardContent } | Next.js 14 / React 18 | Implemented - QA pending | 76

## Backend_Tracker
Service | Controller | Business Logic | Middleware | Authentication | Status | Completion %
Authentication | ApiAuthGuard / AuthSessionService | JWT sessions, role and account status checks | Route guards and cookie security | JWT + password flows | Implemented; security tests pending | 72
Campaign Engine | CampaignExecutionRunner | Preflight, mail merge, credits, locks, retries | Worker ownership and heartbeat | Session-scoped campaign APIs | Implemented; high-risk QA pending | 68
Campaign Scheduler | CampaignQueueScheduler | Queue polling and stale recovery | Worker heartbeat | Worker tick and health endpoints | Implemented; soak tests pending | 66
Mail Delivery | GraphAndSmtpMailSender | Provider dispatch and fallback | Sender resolution | Graph and SMTP | Implemented; provider tests pending | 70
Mailbox | MicrosoftGraphMailboxService | Folders, messages and actions | OAuth token handling | Mailbox and Outlook APIs | Implemented; integration tests pending | 68
Warm-up | WarmupAutoCommunicationService / WarmupAutoReplyService | Conversation scheduling and replies | Rate and safety controls | Warm-up APIs | Implemented; safety QA pending | 60
Billing | SubscriptionCreditService | Credit reset, reserve and ledger | Authenticated ownership | Billing and report APIs | Implemented; reconciliation pending | 65
Client Data | Route-local controllers + validation | Upload, normalize, CRUD, duplicates, bin | Owner scoping | Client data APIs | Implemented; consolidation pending | 70
Analytics | CampaignAnalyticsService | Aggregations and summaries | Authenticated reporting | Dashboard/report APIs | Implemented; metric reconciliation pending | 64
Logging | ActivityLogService | Operational activity records | Actor and owner context | Activity/debug endpoints | Implemented; observability incomplete | 58

## Database_Tracker
Table | Relationships | Indexes | Migration | Seed Data | Completion %
ActivityLogModel | UserProfile | 3 declared index(es) | Schema exists; migration/versioning framework pending | Defaults present; seed script review required | 76
CalendarEvent | UserProfile | 2 declared index(es) | Schema exists; migration/versioning framework pending | Defaults present; seed script review required | 76
Campaign | UserProfile, LeadList, EmailTemplate, EmailDraft | 32 declared index(es) | Schema exists; migration/versioning framework pending | Defaults present; seed script review required | 76
CampaignEmailReply | UserProfile, Campaign, EmailDraft, CampaignRecipientLog | 2 declared index(es) | Schema exists; migration/versioning framework pending | Defaults present; seed script review required | 76
CampaignRecipientClaim | Campaign, LeadList | 1 declared index(es) | Schema exists; migration/versioning framework pending | Defaults present; seed script review required | 76
CampaignRecipientLog | UserProfile, Campaign | 10 declared index(es) | Schema exists; migration/versioning framework pending | Defaults present; seed script review required | 76
CampaignReply | UserProfile, Campaign, LeadList | 2 declared index(es) | Schema exists; migration/versioning framework pending | Defaults present; seed script review required | 76
CampaignSentEmail | UserProfile, Campaign, EmailDraft, CampaignRecipientLog | 2 declared index(es) | Schema exists; migration/versioning framework pending | Defaults present; seed script review required | 76
CampaignWorkerHeartbeat | No explicit Mongoose ref | 1 declared index(es) | Schema exists; migration/versioning framework pending | Defaults present; seed script review required | 76
ClientBinRecord | UserProfile, ClientSheet, ClientRecord, LeadList | 2 declared index(es) | Schema exists; migration/versioning framework pending | Defaults present; seed script review required | 76
ClientRecord | UserProfile, ClientSheet | 5 declared index(es) | Schema exists; migration/versioning framework pending | Defaults present; seed script review required | 76
ClientSheet | UserProfile, LeadList | 6 declared index(es) | Schema exists; migration/versioning framework pending | Defaults present; seed script review required | 76
ConnectedMailAccount | UserProfile | 2 declared index(es) | Schema exists; migration/versioning framework pending | Defaults present; seed script review required | 76
CreditTransaction | Campaign | 1 declared index(es) | Schema exists; migration/versioning framework pending | Defaults present; seed script review required | 76
EmailDraft | UserProfile | 4 declared index(es) | Schema exists; migration/versioning framework pending | Defaults present; seed script review required | 76
EmailTemplate | UserProfile | 2 declared index(es) | Schema exists; migration/versioning framework pending | Defaults present; seed script review required | 76
EmailThread | Campaign, EmailDraft, UserProfile | 1 declared index(es) | Schema exists; migration/versioning framework pending | Defaults present; seed script review required | 76
GraphOAuthAccount | UserProfile | 2 declared index(es) | Schema exists; migration/versioning framework pending | Defaults present; seed script review required | 76
LeadList | UserProfile | 19 declared index(es) | Schema exists; migration/versioning framework pending | Defaults present; seed script review required | 76
MailDraft | UserProfile, Campaign | 1 declared index(es) | Schema exists; migration/versioning framework pending | Defaults present; seed script review required | 76
MailFolderCache | UserProfile | 1 declared index(es) | Schema exists; migration/versioning framework pending | Defaults present; seed script review required | 76
MailMessageCache | UserProfile | 2 declared index(es) | Schema exists; migration/versioning framework pending | Defaults present; seed script review required | 76
MailSyncState | UserProfile | 1 declared index(es) | Schema exists; migration/versioning framework pending | Defaults present; seed script review required | 76
PresetSender | No explicit Mongoose ref | 1 declared index(es) | Schema exists; migration/versioning framework pending | Defaults present; seed script review required | 76
Project | No explicit Mongoose ref | Index review required | Schema exists; migration/versioning framework pending | Defaults present; seed script review required | 65
RecipientSendLock | Campaign, LeadList | Index review required | Schema exists; migration/versioning framework pending | Defaults present; seed script review required | 65
SenderAccount | UserProfile, Project | 9 declared index(es) | Schema exists; migration/versioning framework pending | Defaults present; seed script review required | 76
SenderId | UserProfile, Project | Index review required | Schema exists; migration/versioning framework pending | Defaults present; seed script review required | 65
SignupRequest | No explicit Mongoose ref | 1 declared index(es) | Schema exists; migration/versioning framework pending | Defaults present; seed script review required | 76
TargetApproval | No explicit Mongoose ref | 1 declared index(es) | Schema exists; migration/versioning framework pending | Defaults present; seed script review required | 76
TimelineTask | No explicit Mongoose ref | 4 declared index(es) | Schema exists; migration/versioning framework pending | Defaults present; seed script review required | 76
UpgradeRequest | UserProfile | 2 declared index(es) | Schema exists; migration/versioning framework pending | Defaults present; seed script review required | 76
UploadFile | UserProfile, LeadList | 1 declared index(es) | Schema exists; migration/versioning framework pending | Defaults present; seed script review required | 76
UserProfile | No explicit Mongoose ref | 3 declared index(es) | Schema exists; migration/versioning framework pending | Defaults present; seed script review required | 76
UserSubscription | UserProfile | 1 declared index(es) | Schema exists; migration/versioning framework pending | Defaults present; seed script review required | 76
WarmupAutoReplyLog | No explicit Mongoose ref | 1 declared index(es) | Schema exists; migration/versioning framework pending | Defaults present; seed script review required | 76
WarmupAutoReplySetting | EmailDraft, LeadList | 1 declared index(es) | Schema exists; migration/versioning framework pending | Defaults present; seed script review required | 76
WarmupConversation | UserProfile, WarmupSheet | 3 declared index(es) | Schema exists; migration/versioning framework pending | Defaults present; seed script review required | 76
WarmupMessage | UserProfile, WarmupConversation | 2 declared index(es) | Schema exists; migration/versioning framework pending | Defaults present; seed script review required | 76
WarmupSheet | UserProfile | 3 declared index(es) | Schema exists; migration/versioning framework pending | Defaults present; seed script review required | 76
WorkUpdate | No explicit Mongoose ref | 3 declared index(es) | Schema exists; migration/versioning framework pending | Defaults present; seed script review required | 76

## API_Tracker
API Name | Endpoint | Method | Integrated | Testing Status | Completion %
DELETE /api/accounts/:id | /api/accounts/:id | DELETE | Yes | Automated coverage missing | 72
POST /api/accounts/connect | /api/accounts/connect | POST | Yes | Automated coverage missing | 72
GET /api/accounts | /api/accounts | GET | Yes | Automated coverage missing | 72
POST /api/accounts | /api/accounts | POST | Yes | Automated coverage missing | 72
GET /api/admin/login-accounts | /api/admin/login-accounts | GET | Yes | Automated coverage missing | 72
POST /api/admin/login-accounts | /api/admin/login-accounts | POST | Yes | Automated coverage missing | 72
GET /api/admin/pending-requests | /api/admin/pending-requests | GET | Yes | Automated coverage missing | 72
PATCH /api/admin/upgrade-requests/:id | /api/admin/upgrade-requests/:id | PATCH | Yes | Automated coverage missing | 72
GET /api/admin/upgrade-requests | /api/admin/upgrade-requests | GET | Yes | Automated coverage missing | 72
GET /api/admin/users/:id/campaigns | /api/admin/users/:id/campaigns | GET | Yes | Automated coverage missing | 72
GET /api/admin/users/:id/client-lists | /api/admin/users/:id/client-lists | GET | Yes | Automated coverage missing | 72
GET /api/admin/users/:id/drafts | /api/admin/users/:id/drafts | GET | Yes | Automated coverage missing | 72
PATCH /api/admin/users/:id/reset-password | /api/admin/users/:id/reset-password | PATCH | Yes | Automated coverage missing | 72
GET /api/admin/users/:id | /api/admin/users/:id | GET | Yes | Automated coverage missing | 72
PATCH /api/admin/users/:id/status | /api/admin/users/:id/status | PATCH | Yes | Automated coverage missing | 72
GET /api/admin/users/:id/subscription | /api/admin/users/:id/subscription | GET | Yes | Automated coverage missing | 72
PATCH /api/admin/users/:id/subscription | /api/admin/users/:id/subscription | PATCH | Yes | Automated coverage missing | 72
GET /api/admin/users | /api/admin/users | GET | Yes | Automated coverage missing | 72
POST /api/admin/users | /api/admin/users | POST | Yes | Automated coverage missing | 72
GET /api/alerts | /api/alerts | GET | Yes | Automated coverage missing | 72
POST /api/auth/change-password | /api/auth/change-password | POST | Yes | Automated coverage missing | 72
POST /api/auth/forgot-password | /api/auth/forgot-password | POST | Yes | Automated coverage missing | 72
POST /api/auth/login | /api/auth/login | POST | Yes | Automated coverage missing | 72
POST /api/auth/logout | /api/auth/logout | POST | Yes | Automated coverage missing | 72
GET /api/auth/me | /api/auth/me | GET | Yes | Automated coverage missing | 72
POST /api/auth/request-access | /api/auth/request-access | POST | Yes | Automated coverage missing | 72
POST /api/auth/reset-password | /api/auth/reset-password | POST | Yes | Automated coverage missing | 72
GET /api/billing/invoice | /api/billing/invoice | GET | Yes | Automated coverage missing | 72
POST /api/billing/upgrade | /api/billing/upgrade | POST | Yes | Automated coverage missing | 72
PUT /api/calendar/events/:id | /api/calendar/events/:id | PUT | Yes | Automated coverage missing | 72
DELETE /api/calendar/events/:id | /api/calendar/events/:id | DELETE | Yes | Automated coverage missing | 72
GET /api/calendar/events | /api/calendar/events | GET | Yes | Automated coverage missing | 72
POST /api/calendar/events | /api/calendar/events | POST | Yes | Automated coverage missing | 72
GET /api/campaigns/:id/activity | /api/campaigns/:id/activity | GET | Yes | Automated coverage missing | 72
POST /api/campaigns/:id/clear-logs | /api/campaigns/:id/clear-logs | POST | Yes | Automated coverage missing | 72
GET /api/campaigns/:id/debug | /api/campaigns/:id/debug | GET | Yes | Automated coverage missing | 72
GET /api/campaigns/:id/export | /api/campaigns/:id/export | GET | Yes | Automated coverage missing | 72
POST /api/campaigns/:id/next-step | /api/campaigns/:id/next-step | POST | Yes | Automated coverage missing | 72
POST /api/campaigns/:id/pause | /api/campaigns/:id/pause | POST | Yes | Automated coverage missing | 72
GET /api/campaigns/:id/recipients | /api/campaigns/:id/recipients | GET | Yes | Automated coverage missing | 72
GET /api/campaigns/:id/replies | /api/campaigns/:id/replies | GET | Yes | Automated coverage missing | 72
POST /api/campaigns/:id/replies | /api/campaigns/:id/replies | POST | Yes | Automated coverage missing | 72
POST /api/campaigns/:id/resume | /api/campaigns/:id/resume | POST | Yes | Automated coverage missing | 72
GET /api/campaigns/:id | /api/campaigns/:id | GET | Yes | Automated coverage missing | 72
DELETE /api/campaigns/:id | /api/campaigns/:id | DELETE | Yes | Automated coverage missing | 72
POST /api/campaigns/:id/schedule | /api/campaigns/:id/schedule | POST | Yes | Automated coverage missing | 72
POST /api/campaigns/:id/start | /api/campaigns/:id/start | POST | Yes | Automated coverage missing | 72
GET /api/campaigns/:id/status | /api/campaigns/:id/status | GET | Yes | Automated coverage missing | 72
POST /api/campaigns/:id/stop | /api/campaigns/:id/stop | POST | Yes | Automated coverage missing | 72
POST /api/campaigns/:id/sync-replies | /api/campaigns/:id/sync-replies | POST | Yes | Automated coverage missing | 72
GET /api/campaigns/:id/tracking/:event | /api/campaigns/:id/tracking/:event | GET | Yes | Automated coverage missing | 72
POST /api/campaigns/:id/tracking/:event | /api/campaigns/:id/tracking/:event | POST | Yes | Automated coverage missing | 72
GET /api/campaigns/custom-lists | /api/campaigns/custom-lists | GET | Yes | Automated coverage missing | 72
GET /api/campaigns | /api/campaigns | GET | Yes | Automated coverage missing | 72
POST /api/campaigns | /api/campaigns | POST | Yes | Automated coverage missing | 72
GET /api/campaigns/stats | /api/campaigns/stats | GET | Yes | Automated coverage missing | 72
GET /api/campaigns/tracking/open/:trackingId | /api/campaigns/tracking/open/:trackingId | GET | Yes | Automated coverage missing | 72
UNKNOWN /api/client-bin/restore | /api/client-bin/restore | UNKNOWN | Review required | Automated coverage missing | 40
GET /api/client-bin | /api/client-bin | GET | Yes | Automated coverage missing | 72
POST /api/client-bin | /api/client-bin | POST | Yes | Automated coverage missing | 72
PATCH /api/client-data/:id | /api/client-data/:id | PATCH | Yes | Automated coverage missing | 72
DELETE /api/client-data/:id | /api/client-data/:id | DELETE | Yes | Automated coverage missing | 72
GET /api/client-data/bin | /api/client-data/bin | GET | Yes | Automated coverage missing | 72
PATCH /api/client-data/bin | /api/client-data/bin | PATCH | Yes | Automated coverage missing | 72
POST /api/client-data/bin | /api/client-data/bin | POST | Yes | Automated coverage missing | 72
POST /api/client-data/bulk-delete | /api/client-data/bulk-delete | POST | Yes | Automated coverage missing | 72
UNKNOWN /api/client-data/bulk-save | /api/client-data/bulk-save | UNKNOWN | Review required | Automated coverage missing | 40
PATCH /api/client-data/bulk-update | /api/client-data/bulk-update | PATCH | Yes | Automated coverage missing | 72
POST /api/client-data/create | /api/client-data/create | POST | Yes | Automated coverage missing | 72
PATCH /api/client-data/custom-lists/:id | /api/client-data/custom-lists/:id | PATCH | Yes | Automated coverage missing | 72
DELETE /api/client-data/custom-lists/:id | /api/client-data/custom-lists/:id | DELETE | Yes | Automated coverage missing | 72
GET /api/client-data/custom-lists | /api/client-data/custom-lists | GET | Yes | Automated coverage missing | 72
POST /api/client-data/custom-lists | /api/client-data/custom-lists | POST | Yes | Automated coverage missing | 72
POST /api/client-data/duplicates | /api/client-data/duplicates | POST | Yes | Automated coverage missing | 72
GET /api/client-data/extracted | /api/client-data/extracted | GET | Yes | Automated coverage missing | 72
POST /api/client-data/extracted | /api/client-data/extracted | POST | Yes | Automated coverage missing | 72
PATCH /api/client-data/extracted | /api/client-data/extracted | PATCH | Yes | Automated coverage missing | 72
GET /api/client-data/history | /api/client-data/history | GET | Yes | Automated coverage missing | 72
GET /api/client-data/list | /api/client-data/list | GET | Yes | Automated coverage missing | 72
GET /api/client-data/overview | /api/client-data/overview | GET | Yes | Automated coverage missing | 72
GET /api/client-data/paste-workspace | /api/client-data/paste-workspace | GET | Yes | Automated coverage missing | 72
PUT /api/client-data/paste-workspace | /api/client-data/paste-workspace | PUT | Yes | Automated coverage missing | 72
POST /api/client-data/paste | /api/client-data/paste | POST | Yes | Automated coverage missing | 72
POST /api/client-data/selected-sheet | /api/client-data/selected-sheet | POST | Yes | Automated coverage missing | 72
GET /api/client-data/selected-sheets | /api/client-data/selected-sheets | GET | Yes | Automated coverage missing | 72
GET /api/client-data/sheets | /api/client-data/sheets | GET | Yes | Automated coverage missing | 72
POST /api/client-data/use-for-campaign | /api/client-data/use-for-campaign | POST | Yes | Automated coverage missing | 72
PATCH /api/client-records/:id | /api/client-records/:id | PATCH | Yes | Automated coverage missing | 72
POST /api/client-records/bulk-delete | /api/client-records/bulk-delete | POST | Yes | Automated coverage missing | 72
POST /api/client-records/bulk-update | /api/client-records/bulk-update | POST | Yes | Automated coverage missing | 72
UNKNOWN /api/client-records/bulk | /api/client-records/bulk | UNKNOWN | Review required | Automated coverage missing | 40
POST /api/client-records/detect-duplicates | /api/client-records/detect-duplicates | POST | Yes | Automated coverage missing | 72
POST /api/client-records/move-duplicates-to-bin | /api/client-records/move-duplicates-to-bin | POST | Yes | Automated coverage missing | 72
POST /api/client-sheets/:id/create-selected-list | /api/client-sheets/:id/create-selected-list | POST | Yes | Automated coverage missing | 72
GET /api/client-sheets/:id | /api/client-sheets/:id | GET | Yes | Automated coverage missing | 72
PATCH /api/client-sheets/:id | /api/client-sheets/:id | PATCH | Yes | Automated coverage missing | 72
DELETE /api/client-sheets/:id | /api/client-sheets/:id | DELETE | Yes | Automated coverage missing | 72
POST /api/client-sheets/:id/rows | /api/client-sheets/:id/rows | POST | Yes | Automated coverage missing | 72
GET /api/client-sheets | /api/client-sheets | GET | Yes | Automated coverage missing | 72
POST /api/client-sheets | /api/client-sheets | POST | Yes | Automated coverage missing | 72
POST /api/client-sheets/upload | /api/client-sheets/upload | POST | Yes | Automated coverage missing | 72
GET /api/credits | /api/credits | GET | Yes | Automated coverage missing | 72
GET /api/dashboard/activity | /api/dashboard/activity | GET | Yes | Automated coverage missing | 72
GET /api/dashboard/overview | /api/dashboard/overview | GET | Yes | Automated coverage missing | 72
POST /api/draft-file-text | /api/draft-file-text | POST | Yes | Automated coverage missing | 72
GET /api/drafts/:id | /api/drafts/:id | GET | Yes | Automated coverage missing | 72
PATCH /api/drafts/:id | /api/drafts/:id | PATCH | Yes | Automated coverage missing | 72
DELETE /api/drafts/:id | /api/drafts/:id | DELETE | Yes | Automated coverage missing | 72
GET /api/drafts | /api/drafts | GET | Yes | Automated coverage missing | 72
POST /api/drafts | /api/drafts | POST | Yes | Automated coverage missing | 72
GET /api/graph-oauth/callback | /api/graph-oauth/callback | GET | Yes | Automated coverage missing | 72
GET /api/graph-oauth/start | /api/graph-oauth/start | GET | Yes | Automated coverage missing | 72
GET /api/health | /api/health | GET | Yes | Automated coverage missing | 72
POST /api/leads/create-campaign | /api/leads/create-campaign | POST | Yes | Automated coverage missing | 72
GET /api/leads/pipeline | /api/leads/pipeline | GET | Yes | Automated coverage missing | 72
POST /api/lists/:id/normalize-emails | /api/lists/:id/normalize-emails | POST | Yes | Automated coverage missing | 72
GET /api/lists/:id | /api/lists/:id | GET | Yes | Automated coverage missing | 72
PATCH /api/lists/:id | /api/lists/:id | PATCH | Yes | Automated coverage missing | 72
DELETE /api/lists/:id | /api/lists/:id | DELETE | Yes | Automated coverage missing | 72
POST /api/lists/custom | /api/lists/custom | POST | Yes | Automated coverage missing | 72
GET /api/lists | /api/lists | GET | Yes | Automated coverage missing | 72
GET /api/mail-overview | /api/mail-overview | GET | Yes | Automated coverage missing | 72
GET /api/mailbox-folders | /api/mailbox-folders | GET | Yes | Automated coverage missing | 72
GET /api/mailbox/accounts | /api/mailbox/accounts | GET | Yes | Automated coverage missing | 72
GET /api/mailbox/folders | /api/mailbox/folders | GET | Yes | Automated coverage missing | 72
POST /api/mailbox/forward | /api/mailbox/forward | POST | Yes | Automated coverage missing | 72
POST /api/mailbox/messages/:id/archive | /api/mailbox/messages/:id/archive | POST | Yes | Automated coverage missing | 72
POST /api/mailbox/messages/:id/delete | /api/mailbox/messages/:id/delete | POST | Yes | Automated coverage missing | 72
POST /api/mailbox/messages/:id/mark-read | /api/mailbox/messages/:id/mark-read | POST | Yes | Automated coverage missing | 72
GET /api/mailbox/messages/:id | /api/mailbox/messages/:id | GET | Yes | Automated coverage missing | 72
GET /api/mailbox/messages | /api/mailbox/messages | GET | Yes | Automated coverage missing | 72
POST /api/mailbox/reply | /api/mailbox/reply | POST | Yes | Automated coverage missing | 72
POST /api/mailbox/send | /api/mailbox/send | POST | Yes | Automated coverage missing | 72
GET /api/outlook/accounts | /api/outlook/accounts | GET | Yes | Automated coverage missing | 72
POST /api/outlook/archive | /api/outlook/archive | POST | Yes | Automated coverage missing | 72
UNKNOWN /api/outlook/callback | /api/outlook/callback | UNKNOWN | Review required | Automated coverage missing | 40
UNKNOWN /api/outlook/connect | /api/outlook/connect | UNKNOWN | Review required | Automated coverage missing | 40
POST /api/outlook/delete | /api/outlook/delete | POST | Yes | Automated coverage missing | 72
POST /api/outlook/draft | /api/outlook/draft | POST | Yes | Automated coverage missing | 72
UNKNOWN /api/outlook/folders | /api/outlook/folders | UNKNOWN | Review required | Automated coverage missing | 40
UNKNOWN /api/outlook/forward | /api/outlook/forward | UNKNOWN | Review required | Automated coverage missing | 40
POST /api/outlook/mark-read | /api/outlook/mark-read | POST | Yes | Automated coverage missing | 72
UNKNOWN /api/outlook/message/:id | /api/outlook/message/:id | UNKNOWN | Review required | Automated coverage missing | 40
UNKNOWN /api/outlook/messages | /api/outlook/messages | UNKNOWN | Review required | Automated coverage missing | 40
UNKNOWN /api/outlook/reply | /api/outlook/reply | UNKNOWN | Review required | Automated coverage missing | 40
UNKNOWN /api/outlook/send | /api/outlook/send | UNKNOWN | Review required | Automated coverage missing | 40
POST /api/preset-senders | /api/preset-senders | POST | Yes | Automated coverage missing | 72
GET /api/profile/overview | /api/profile/overview | GET | Yes | Automated coverage missing | 72
POST /api/profile/password | /api/profile/password | POST | Yes | Automated coverage missing | 72
GET /api/profile | /api/profile | GET | Yes | Automated coverage missing | 72
PATCH /api/profile | /api/profile | PATCH | Yes | Automated coverage missing | 72
GET /api/projects | /api/projects | GET | Yes | Automated coverage missing | 72
GET /api/reports/credits | /api/reports/credits | GET | Yes | Automated coverage missing | 72
GET /api/reports/overview | /api/reports/overview | GET | Yes | Automated coverage missing | 72
GET /api/reports/project-wise | /api/reports/project-wise | GET | Yes | Automated coverage missing | 72
GET /api/reports/sender-health | /api/reports/sender-health | GET | Yes | Automated coverage missing | 72
GET /api/reports/warmup | /api/reports/warmup | GET | Yes | Automated coverage missing | 72
POST /api/send-test | /api/send-test | POST | Yes | Automated coverage missing | 72
GET /api/sender-ids | /api/sender-ids | GET | Yes | Automated coverage missing | 72
POST /api/sender-ids | /api/sender-ids | POST | Yes | Automated coverage missing | 72
GET /api/stats | /api/stats | GET | Yes | Automated coverage missing | 72
GET /api/subscription | /api/subscription | GET | Yes | Automated coverage missing | 72
POST /api/subscription/upgrade | /api/subscription/upgrade | POST | Yes | Automated coverage missing | 72
GET /api/target-approval | /api/target-approval | GET | Yes | Automated coverage missing | 72
PATCH /api/target-approval | /api/target-approval | PATCH | Yes | Automated coverage missing | 72
PATCH /api/tasks/:id | /api/tasks/:id | PATCH | Yes | Automated coverage missing | 72
DELETE /api/tasks/:id | /api/tasks/:id | DELETE | Yes | Automated coverage missing | 72
GET /api/tasks | /api/tasks | GET | Yes | Automated coverage missing | 72
POST /api/tasks | /api/tasks | POST | Yes | Automated coverage missing | 72
GET /api/templates | /api/templates | GET | Yes | Automated coverage missing | 72
POST /api/templates | /api/templates | POST | Yes | Automated coverage missing | 72
POST /api/timeline-tasks/:id/complete | /api/timeline-tasks/:id/complete | POST | Yes | Automated coverage missing | 72
POST /api/timeline-tasks/:id/note | /api/timeline-tasks/:id/note | POST | Yes | Automated coverage missing | 72
POST /api/timeline-tasks/:id/reassign | /api/timeline-tasks/:id/reassign | POST | Yes | Automated coverage missing | 72
PATCH /api/timeline-tasks/:id | /api/timeline-tasks/:id | PATCH | Yes | Automated coverage missing | 72
DELETE /api/timeline-tasks/:id | /api/timeline-tasks/:id | DELETE | Yes | Automated coverage missing | 72
GET /api/timeline-tasks | /api/timeline-tasks | GET | Yes | Automated coverage missing | 72
POST /api/timeline-tasks | /api/timeline-tasks | POST | Yes | Automated coverage missing | 72
POST /api/uploads/commit | /api/uploads/commit | POST | Yes | Automated coverage missing | 72
POST /api/uploads/preview | /api/uploads/preview | POST | Yes | Automated coverage missing | 72
POST /api/uploads | /api/uploads | POST | Yes | Automated coverage missing | 72
GET /api/uploads | /api/uploads | GET | Yes | Automated coverage missing | 72
GET /api/warmup-auto-reply | /api/warmup-auto-reply | GET | Yes | Automated coverage missing | 72
POST /api/warmup-auto-reply | /api/warmup-auto-reply | POST | Yes | Automated coverage missing | 72
GET /api/warmup-dashboard | /api/warmup-dashboard | GET | Yes | Automated coverage missing | 72
POST /api/warmup-dashboard | /api/warmup-dashboard | POST | Yes | Automated coverage missing | 72
GET /api/warmup/conversations | /api/warmup/conversations | GET | Yes | Automated coverage missing | 72
GET /api/warmup/drafts | /api/warmup/drafts | GET | Yes | Automated coverage missing | 72
GET /api/warmup/leads | /api/warmup/leads | GET | Yes | Automated coverage missing | 72
GET /api/warmup/logs | /api/warmup/logs | GET | Yes | Automated coverage missing | 72
POST /api/warmup/pause | /api/warmup/pause | POST | Yes | Automated coverage missing | 72
GET /api/warmup/projects | /api/warmup/projects | GET | Yes | Automated coverage missing | 72
POST /api/warmup/run-next | /api/warmup/run-next | POST | Yes | Automated coverage missing | 72
GET /api/warmup/senders | /api/warmup/senders | GET | Yes | Automated coverage missing | 72
GET /api/warmup/sheets | /api/warmup/sheets | GET | Yes | Automated coverage missing | 72
POST /api/warmup/sheets | /api/warmup/sheets | POST | Yes | Automated coverage missing | 72
POST /api/warmup/sheets/upload | /api/warmup/sheets/upload | POST | Yes | Automated coverage missing | 72
POST /api/warmup/start-auto-communication | /api/warmup/start-auto-communication | POST | Yes | Automated coverage missing | 72
POST /api/warmup/start | /api/warmup/start | POST | Yes | Automated coverage missing | 72
POST /api/warmup/stop | /api/warmup/stop | POST | Yes | Automated coverage missing | 72
POST /api/warmup/upload | /api/warmup/upload | POST | Yes | Automated coverage missing | 72
PATCH /api/work-updates/:id | /api/work-updates/:id | PATCH | Yes | Automated coverage missing | 72
DELETE /api/work-updates/:id | /api/work-updates/:id | DELETE | Yes | Automated coverage missing | 72
GET /api/work-updates | /api/work-updates | GET | Yes | Automated coverage missing | 72
POST /api/work-updates | /api/work-updates | POST | Yes | Automated coverage missing | 72
GET /api/worker-health | /api/worker-health | GET | Yes | Automated coverage missing | 72
GET /api/worker/tick | /api/worker/tick | GET | Yes | Automated coverage missing | 72
POST /api/worker/tick | /api/worker/tick | POST | Yes | Automated coverage missing | 72

## Bug_Tracker
Bug ID | Module | Severity | Assigned To | ETA | Status
BUG-001 | Engineering Quality | Critical | Akshay / Full-stack | 25-06-2026 | Open - ESLint configuration missing
BUG-002 | Schedule Workflow | High | Akshay / Full-stack | 24-06-2026 | In Progress - build verification interrupted
BUG-003 | Responsive UI | High | Akshay / Full-stack | 05-07-2026 | Open - manual viewport matrix incomplete
BUG-004 | Automated Testing | Critical | Akshay / Full-stack | 10-07-2026 | Open - no product test suite
BUG-005 | Campaign Engine | Critical | Akshay / Full-stack | 21-07-2026 | Risk - duplicate-send and recovery proof missing
BUG-006 | Legacy Campaign Engine | Medium | Akshay / Full-stack | 10-09-2026 | Open - unresolved msal dependency in legacy service

## Testing_Tracker
Feature | Unit Test | Integration Test | Manual Test | UAT | Status
Authentication and RBAC | Missing | Missing / not evidenced | Required | Not started | Red
Dashboard and role workspaces | Missing | Missing / not evidenced | Partial | Not started | Red
Client data and lead lists | Missing | Missing / not evidenced | Required | Not started | Red
Drafts and templates | Missing | Missing / not evidenced | Required | Not started | Red
Campaign workflow | Missing | Missing / not evidenced | Required | Not started | Red
Campaign execution worker | Missing | Missing / not evidenced | Required | Not started | Red
Sender accounts and OAuth | Missing | Missing / not evidenced | Required | Not started | Red
Unified mailbox | Missing | Missing / not evidenced | Required | Not started | Red
Warm-up automation | Missing | Missing / not evidenced | Required | Not started | Red
Reports and analytics | Missing | Missing / not evidenced | Required | Not started | Red
Admin and subscriptions | Missing | Missing / not evidenced | Required | Not started | Red
Tasks, calendar and productivity | Missing | Missing / not evidenced | Required | Not started | Red
Observability and operations | Missing | Missing / not evidenced | Required | Not started | Red
Automated QA | Missing | Missing / not evidenced | Required | Not started | Red
CI/CD and deployment | Missing | Missing / not evidenced | Required | Not started | Red

## Deployment_Tracker
Environment | Frontend Version | Backend Version | Database Version | Status
Local Development | Next.js 14.2.5 working tree | App Router APIs + worker | MongoDB/Mongoose 8.18 schemas | Active; lint setup missing
Local Production Build | Pending clean rebuild | Pending clean rebuild | Shared development DB | Build was interrupted on 2026-06-23
Staging ECS | Not verified | Web + worker templates exist | MongoDB Atlas expected | Planned
Production ECS | Not released from this baseline | Not released from this baseline | Backup/restore proof pending | Not ready

## Risks_And_Blockers
Risk Type | Description | Severity | Owner | Mitigation Plan | Status
Quality | No committed ESLint configuration; lint prompts interactively | High | Akshay / Full-stack | Add config, baseline violations, enforce in CI | Open
Testing | Only utility/diagnostic scripts found; no meaningful automated product suite | Critical | Akshay / Full-stack | Implement test pyramid and release gates | Open
Delivery Safety | Campaign concurrency, stale recovery and recipient dedupe are high-impact | Critical | Akshay / Full-stack | Crash, race, retry and duplicate-send test matrix | Open
Security | Broad auth, OAuth and mailbox surface needs systematic security validation | Critical | Akshay / Full-stack | OWASP review, token/secret audit, negative tests | Open
Maintainability | PremiumDashboardShell.jsx and globals.css are very large and change-prone | High | Akshay / Full-stack | Split by domain and reduce global override debt | Open
Data Reliability | 39 models without formal migration/versioning framework | High | Akshay / Full-stack | Migration registry, backups, restore rehearsal | Open
Operations | Worker/web separation exists in docs but staging proof is incomplete | High | Akshay / Full-stack | ECS staging deployment and failure drills | Open
Scope | One full-stack owner is carrying product, QA, DevOps and PM responsibilities | High | Project Sponsor | Add QA/reviewer capacity or extend dates | Open
Legacy | Multiple legacy runtimes can cause confusion and dependency/security drift | Medium | Akshay / Full-stack | Archive or decommission after production parity | Open
Planning | Progress percentages are evidence-based estimates, not measured time-sheet data | Medium | Akshay / Full-stack | Update Daily_Updates with actual hours and acceptance evidence | Accepted for baseline

## Team_Productivity
Developer | Tasks Completed | Hours Worked | Productivity Score | This Week Completed | This Week Updated | Next Week Focus | Remarks
Akshay / Full-stack | 2 |  | Baseline pending actual-hours input | IMP-001: Create durable project baseline and Google Sheets import pack ¦ IMP-034: Fix Excel and Google Sheets import date formatting and weekly auto-fill summaries | IMP-002: Finish four-column schedule details layout and six-column delivery settings ¦ IMP-008: Harden XLSX/CSV upload, preview, commit and validation errors ¦ IMP-009: Verify bulk edit/delete, duplicate detection, bin and restore workflows ¦ IMP-030: Execute manual QA at 320, 375, 430, 768, 1024, 1280, 1440 and 1920 pixels ¦ IMP-003: Commit a non-interactive ESLint configuration and resolve baseline violations ¦ IMP-004: Run clean production build and document warnings ¦ IMP-005: Define test pyramid, fixtures, environments, and release gates ¦ IMP-006: Automate login, logout, session, role routing, pending and disabled account flows ¦ IMP-007: Audit cookie flags, JWT expiry, token crypto, password reset and secret handling | IMP-006: Automate login, logout, session, role routing, pending and disabled account flows ¦ IMP-007: Audit cookie flags, JWT expiry, token crypto, password reset and secret handling ¦ IMP-008: Harden XLSX/CSV upload, preview, commit and validation errors ¦ IMP-009: Verify bulk edit/delete, duplicate detection, bin and restore workflows ¦ IMP-010: Stabilize draft editor, templates, file text extraction and preview ¦ IMP-011: Validate audience, sender, content, credits and scheduling before creation ¦ IMP-012: Test queue, locks, heartbeat, stale recovery, pause, resume, stop and completion ¦ IMP-030: Execute manual QA at 320, 375, 430, 768, 1024, 1280, 1440 and 1920 pixels | Do not infer productivity from commit count; record actual hours and accepted outputs daily.